NHS Golden Jubilee

Board Meeting

28 May 2020

- Board Risk Register Update

Prepared by Laura Langan, Head of Risk & Clinical Governance

1.	Situation

This paper presents an update following review of the Board Risk Register, highlighting any changes in risk level and new risks.

2. 	Background

The Board previously accepted 3 new risks onto the Board Risk Register as follows which have been added:

The three new risks being proposed relate to:

- Employee health and wellbeing during the COVID-19 response and into the recovery period

- Provision of adequate PPE to ensure employee health and safety during the COVID-19 response and into the recovery period

- Ensuring that we maximise utilization of GJNH capacity

A further review of all risks on the Board register has been undertaken via Executive leads with the mitigations both current and planned updated, section three highlights where risk levels have changed and a further new risk being proposed.

Separate to the Board Risk Register there is work underway to risk assess the recovery plan supporting the COVID-19 response.  This is part of the mitigation in response to the new risk relating to underutilization and will include development of risk register specific to work streams including specialties and also a general workforce risk register.  As part of the recovery planning a review of the governance and reporting structure is being considered which will include the risk reporting.

3. 	 Assessment

Risk Register Changes

It is recommended that the following risk levels are revised:

O9 Failure to meet SLA and waiting times activity targets

Proposal increase to L 5 x S 3 = 15 HIGH

This risk was previously a likelihood of 3, give the impact of the COVID-19 on elective core services this risk is being realised.  The recovery plan and AOP revisions form the main mitigations in resolving this.

S11 Inability to achieve the objectives of the Expansion programme

Proposal increase to L 4 x S 4 = 16 HIGH

A review of the risk registers for both phases has been undertaken.  It is proposed that for each phase a new risk is added to reflect the impact of the COVID-19 pandemic.  Whilst this is impacting on both phases in different ways due to the different stages it is felt this is a Very High risk for both at the present time.  An additional new risk has been proposed in relation to ensuring alignment between the recovery plan and the Phase 2 expansion programme reflecting the change in planned use of the site over the recovery period and need to be mindful of how the phase 2 orthopaedic and general surgery expansion aligns to this.

S16 If we don’t secure appropriate ICD support to the project then it will impact on the project in terms of key decisions and timelines

Proposal reduce to L 2 x S 4 = *MEDIUM

Consultant microbiologist appointment has been made internally due to commence in May with additional with Microbiologist Consultant support to expansion and a national appointment with sessional input to GJ to be confirmed.  Once these posts are in place and microbiology review of FBC for stage 2 is complete it is proposed to remove the risk but given progress it is suggested likelihood is reduced to a medium at present.

A further new risk relating to the COVID-19 is proposed as follows:

Ongoing impact and potential of a further peak of COVID-19 pandemic across Board

Proposal – L 4 x S 3 = 12 HIGH

This risk is to capture the potential ongoing impact of COVID-19 across the Foundation including the hotel and the wider impact on the Board strategy; this encapsulate the impact of the delays in the immediate pandemic period, ongoing restrictions and potential of a further peak which would mean a return to stricter measures indefinitely.  Mitigations include the Command Structure in place to support the response, recovery plan development as well as the specific risks that have been generated in response to the situation.  Planned mitigations reflect the work ongoing to implement the recovery plan, social distancing work across the Board which includes review of the site masterplan to support this, review of the Board Strategic Programmes and the Hotel Strategy review to reflect the specific impact to the hotel operations.

Risk Profile & Appetite

|  | Hospital | Hotel | R&D | Innovation |
| --- | --- | --- | --- | --- |
| Strategic | Willing | Moderate | Open | Willing |
| Safety/ Experience | Cautious | Cautious | Cautious | Moderate |
| Reputation | Open | Moderate | Moderate | Moderate |
| Financial | Moderate | Willing | Open | Open |
| Regulation | Cautious | Moderate | Cautious | Moderate |
| Operational | Moderate | Open | Cautious | Open |
| Workforce | Moderate | Open | Open | Open |

Board Risk Register HEAT Map

| Likelihood | Consequence/ Impact |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 |
| 5 |  |  | O9 |  |  |
| 4 |  |  | S12: S17:S20 | S11 |  |
| 3 |  | S14 | S3:: O15: | S10: S13: W7: W19 |  |
| 2 |  |  | F8: W18 | S16: S6: |  |
| 1 |  |  |  |  |  |

In considering the risk appetite, the majority of risks sit within or at the appetite level with the exception of the workforce risks.  Risk appetite for workforce is Moderate and W7 (Workforce Capacity and Capability) and W19 (PPE Provision) currently sit with a severity of 4. At present both have a likelihood of 3 with mitigation planned to reduce to a likelihood of 2.

4. 	 Recommendation

Member are asked to:

- Discuss the recommended changes in risk grading

- Support the new risk proposed

- Note the Workforce risks are outwith appetite

| Ref | Risk Title & Impact Summary | Risk Owner |  | Current Risk Rating |  |  |  |  |  | Current Mitigations |  | Risk Target |  |  |  |  |  | Planned Mitigation |  | Risk Review Freq |  | Date last updated |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Likelihood |  | Severity |  | Risk Level |  |  |  | Likelihood |  | Severity |  | Risk Level |  |  |  |  |  |  |  |  |
| S3 | If we do not ensure a robust framework to support innovation at local, national and international level Strategic – Vision of leading quality, innovation & research not achieved Financial - potential for financial penalties, missed opportunity for income generation Regulatory – ensuring compliance with NHSScotland standards. Reputational – damage to GJF brand and impact on SG and NHSScotland Safety/ Experience – ensuring protection of staff & patients involved, missed opportunity to improve safety/ experience | AH |  | 3 |  | 3 |  | 9 |  | Executive Director of Finance and Senior Planning Officer supporting the delivery of the vision and purpose. Ensuring alignment of vision and values in supporting culture of innovation within GJ Strategic Partnerships (SP) Framework and new Policy endorsed and agreed by NHS GJ Board - now implemented and followed ref: all SP. External and Internal Short-Life Working Group established (GJ, Scottish Enterprise, University of Strathclyde, Scottish Government, |  | 2 |  | 3 |  | 6 |  | Development of Innovation Accelerator Business Case to be delivered by 30 June 2020 Establishing clear options for the delivery of Phase 3 Working with new Framework and Policy but bring back to the Board for a recalibration Dec 2020 |  | Bi monthly |  | April 20 |  |  |
| S6 | Susceptibility to Healthcare Associated Infection events, including pandemic, impacting delivery of corporate objectives Strategic- unlikely to be change in strategic intent Financial: Unlikely to significantly affect delivery of financial targets. Regulation: no significant issues associated with this Reputation: Prevalence of HAI within GJF would damage the Board’s reputation Operational Delivery: HAI has the potential to negatively impact patient clinical outcomes and also affect operational delivery through events such as ward closures threatening SLA delivery. Workforce: Increased incidence of HAI may negatively impact staff both morale and productivity through ward closures and additional scrutiny | AMC |  | 2 |  | 4 |  | 8 |  | Annual work plan approved and progress monitored at PICC meeting; Surveillance in place for - Monitoring of alert organisms; - Surgical site infection; - Enhanced SAB surveillance; - E-Coli; Appropriate clinical risk assessment and patient screening for MRSA and CPE; Monitoring and analysis of HEAT target data for SAB and CDI supported by multidisciplinary reduction interventions; SCNs fully engaged via weekly visits and monthly peer reviews and HEI preparedness committee; HAI reports presented to all relevant Board and management committees HAI Scribe process in place that ensures Infection Control built in to all building / estates issues. M.chimera monitoring. |  | 2 |  | 4 |  | 8 |  | Continue to monitor via existing controls Board Microbiologist appointment in May. |  | Bi-Monthly |  | April 20 |  |  |
| W7 | Insufficient workforce capability and capacity to support corporate objectives Strategic: Unlikely to be any significant strategic change workforce planning Financial: may have an impact on use of agency, locum or waiting list initiative payments to cover short term gaps Regulation: Unlikely to affect regulation Reputation: Potential impact on recruitment. Operational Delivery: lack of appropriately trained staff would undermine the Board’s ability to operate. Workforce: Staff dissatisfaction due to increased workload pressure; increasing risk of staff absence and turnover and with further loss of skills and knowledge. | GA |  | 3 |  | 4 |  | 12 |  | Annual Workforce Plan and workforce monitoring report Values Steering Group in place to support workforce culture Spiritual care service support to staff Recruitment data monitored on a regular basis and presented to the Board twice a year via the Workforce Monitoring Report; Full programme of training and education reviewed annually and underpinned by training needs analysis across the Board; and Board local HR/strategic policy mirrors national guidance and policy on terms and conditions. Approved Phase 1 expansion workforce plan Draft Phase 2 expansion workforce plan Draft health and wellbeing action plan in response to covid outbreak PPE monitoring and management controls |  | 2 |  | 4 |  | 8 |  | New approach to workforce planning to be established in 2019/2020 to support longer term planning and new national approach to 3-year workforce planning to be introduced in 2021 Phase 2 expansion workforce plan currently being finalised New Staff Health & Wellbeing Strategy in development, delayed due to covid but planned for late spring early summer – draft action plan in response to covid already developed. NHS Scotland Academy proposal to be developed to support expansion of elective care and NHS workforce Participation in national elective centres workforce planning group to plan national demand for workforce Recovery workforce plan to be developed. |  | Bi Monthly |  | April 20 |  |  |
| F8 | Failure to deliver the Board’s financial plan and maximise effective use of the Board’s resources and assets Strategic: Risk in strategic decision making that impacts on financial position Financial: Failure to deliver financial targets would result in a recovery plan being put in place with a likely impact on services Reputation: Failure to deliver financial targets would damage the Board’s reputation as an effective healthcare provider with SGHD and with the public. Operational Delivery: Recovery plan is likely to impact on some operational delivery. Non clinical vacant posts would be held, reviews of stock, purchasing and services would be undertaken . Workforce: Would impact on vacancies in non clinical posts and possible skill mix reviews of clinical services | CN |  | 2 |  | 3 |  | 6 |  | 2020-21 financial plan submitted with plans to achieve financial balance Efficiency and productivity plans being progressed Specific risks highlighted within the financial plan are being closely monitored; Monthly financial reviews are in place to identify any variations from the plan; PRG’s set with Divisions and all departments in NHSGJ on a regular basis With regards to Covid 19 pandemic – Mobilisation plans agreed with SG and a subsequent Recovery Plan has been constructed and financial impact incorporated in financial planning assumptions and shared with SG. Principles on income and funding agreed in principal, pending final recovery plan agreement A detailed forecast will be produced from month 3 onwards to aid a balanced financial position to be delivered for the year, by taking corrective action as required and raise via management and governance meetings. Finance, Performance and Planning Committee now embedded with supporting monitoring reports including IPR and Financial Report updates. |  | 2 |  | 3 |  | 6 |  | Ongoing rigorous monitoring of financial position. Financial position and forecasts presented to Senior Management Team and Board on a monthly basis. Regular communications with Scottish Government on operational and financial performance where transparency on financial and operational requirements are defined through robust communication and understanding on inputs / outputs. |  | Bi Monthly |  | April 20 |  |  |
| O9 | Failure to meet SLA and waiting times activity targets Strategic: All activity severely impacted by COVID-19; elective activity suspended by SG. Financial: Failure to deliver operational targets may lead to loss of income but likely to be minimal impact Regulation: TTG breaches, need to ensure compliance with COVID-19 measures. Reputation: Seen as unable to deliver operational targets and negative impact on reputation Operational Delivery: review of pathways and capacity would be undertaken and a recovery plan put in place. Workforce: impact on existing services to increase capacity to support recovery plan. | JR |  | 5 |  | 3 |  | 15 |  | Waiting Time pressures are monitored within the Divisional Operational Team, at weekly and monthly operational meetings Revised Integrated Performance Report implemented to support deep dive of any areas outwith expected performance. Reported to SMT and F,P&P. Engagement with referring Boards continues with a national Leads meeting established. |  | 1 |  | 3 |  | 3 |  | Recovery plan to be submitted to SG to support activity ove1 -2 year period. Implementation of recovery plan via liaison with NHSBoards. Review of AOP to incorporate definition of financial flows for 2020/21. Revised governance and monitoring structure to be agreed to monitor progress of recovery plan. |  | Bi Monthly |  | April 20 |  |  |
| S10 | Information and Technology resilience to potential IT security breaches and attacks Strategic: Decision making exposes risk to Board Financial: Potential for financial impact should a breach occur. Regulation: Potential for sanctions and, or litigation should a breach occur. Reputation: A data security breach is likely to negatively impact GJF’s reputation and damage brand perception among patients, the media and Scottish Government. Operational Delivery: Disrupted access to electronic systems such as TrakCare and SCI would impact day to day operations in wards, clinics, theatres and admin functions resulting in disrupted patient care and loss of productivity. Workforce: Unlikely to affect workforce significantly | CN |  | 3 |  | 4 |  | 12 |  | Information Technology security measures and controls are in place across the organisation and supported by the wider NHS network; Further controls implemented following recent IT security attacks on private sector organisations; Board wide review of information security established with self assessment against NHS Scotland IT Security Framework completed and action plan developed; and Realtime cyber attack took place with the Board not infected. Internal and external controls were tested with a formal debrief highlighting some lessons learnt. These have been implemented. A Cyber Security maturity review was undertaken by PwC; Cyber essentials Accreditation gained Oct 18 and reviewed annually. |  | 2 |  | 4 |  | 8 |  | Ongoing rigorous monitoring of controls and action plan via regular updates to Information Governance Group. |  | Quarterly |  | April 20 |  |  |
| S11 | Inability to achieve the objectives of the Expansion programme Strategic: Key strategic objective, ability to deliver wider commitments of programme and added value at national level. Impacts on national government strategy of failure to deliver. Financial: Potential for financial impact should a breach occur. VFM. Regulation: Need to ensure new facilities are compliant with COVID-19 precautions during construction and on opening. Reputation: negative impact on brand/ reputation and credibility of clinical models if unable to deliver. Operational Delivery: Ability to deliver TTG and operational demands. Workforce: importance of developing workforce to support programme; failure to deliver would impact on this. Unkowns can impact workforce planning. | JR |  | 4 |  | 4 |  | 16 |  | National Programme Board chaired by Chief Executive Project Team in place with project plan and key milestones agreed; supporting governance structure in place for programme. Risk appetite developed for programme to support discussion on tolerance and escalation of risk and risk framework in place. FBC approved for stage 1 & IA approval or Stage 2 Clinically led design for both phases with plans for organisational development support aligned to programme. |  | 2 |  | 3 |  | 6 |  | Ongoing discussions with PSCP to evaluate impact of COVID-19 and recovery plan. Revised timeline for Phase 1 and Phase 2 to be agreed once quantified. Revised plan to support OBC Approval for Stage 2. Ensure alignment of Phase 2 plans with wider GJNH recovery plan. Board Microbiologist appointment in May, Microbiologist Consultant support to expansion and national appointment with sessional input to GJ |  | Monthly |  | April 20 |  |  |
| S12 | The impact of EU Withdrawal on the Boards ability to continue to meet its corporate objectives Strategic: ability to deliver corporate objectives and on long term strategy Financial: Financial consequences possible in relation to funding and budget impact. Regulation: impact as EU regs transferred; loss of access to MHRA; R&D impact of not being part of EU Reputation: not specific to GJF Operational Delivery: pharmaceutical and market impacts that may affect supplies of key items Workforce: high risk areas within medical staffing and hotel housekeeping identified | AMC |  | 4 |  | 3 |  | 12 |  | Brexit Horizon scan commenced 2015 and updated regularly. Preparedness assessment undertaken for SG supported by existing work and key risk areas identified and monitoring arrangements confirmed. Executive and Operational Leads agreed to oversee. |  | 2 |  | 2 |  | 4 |  | SLWG established with input from key areas. Group stepped down at present with virtual updates ad will be reconvened as required with direct report to Executive Group. Links made to national contingencies. |  | Quarterly |  | April 20 |  |  |
| S14 | If we do not fully achieve the EPR programme within timescale there is potential for impact on corporate objectives, namely the hospital expansion Strategic: potential impact on expansion programme, designed for EPR environment; failure to realise benefits of programme and objective Financial: Potential costs associated in additional spend; impact on value for money if benefits not fully realised Reputation: potential for impact on GJ reputation Operational Delivery: Could vary from little impact to moderate if system issues Workforce: Impact on future workforce plans if not realised; low morale amongst staff may impact on engagement with system; education & awareness needs Safety/ Experiences Benefits not realised | JR |  | 3 |  | 2 |  | 6 |  | EPR Programme Board chaired by Executive Lead. EPR Operational Group in place. EPR Team consisting of E-Health and seconded clinical staff in place. Syncrophi, OrderComms, Medicines Management implementations underway as part of wider project. Risk Register in place; master supported by operational level. Revised project plan with agreement to pilot on ophthalmology and orthopaedics then review. |  | 2 |  | 1 |  | 2 |  | Implementation of phase 1 with ophthalmology and orthopaedic pathways. Business case to support further development across remaining specialties. |  | Bi Monthly |  | April 20 |  |  |
| O15 | Impact of ongoing clinical waste management in absence of national contract Strategic: potential to impact of delivery of service Financial: additional costs incurred by contingency Regulation: breach in handling/ storage regulations could result in action Reputation: impact on GJF reputation Operational Delivery: Contingency impact to portering service and waste service to clinical areas Workforce: impact on porters undertaking role long term; ability to sustain long term | AMC |  | 3 |  | 3 |  | 9 |  | Major Incident Procedure activated to support initial response. SLWG continuing to meet and review led by Nurse Director. Contingencies in place with waste bagged and placed in secure clinical waste area then uplifted by porters and transferred to an articulated lorry located at the loading bay. This is uplifted and replaced as required generally every 2-3 days. A risk assessment has been undertaken with support from staff and partnerships. Waste Officer participating in regular calls with NSS to monitor and update on situation. |  |  |  |  |  |  |  | Implementation of revised national contract – plans in place to support including review of Waste Policy and processes to support. Overview of compliance to be maintained via H&S Committee. |  | Bi Monthly |  | April 20 |  |  |
| S16 | If we don’t secure appropriate ICD support to the project then it will impact on the project in terms of key decisions and timelines Strategic: could impact on quality of outputs and overall achievement of project which would impact GJF and wider West of Scotland region. Financial: financial impact associated with late or non delivery of key project objectives. Post construction, lack of ICD support during design or could lead to further control measures required to rectify infection incidents related to the built environment. Reputation: Negative impact on reputation of GJF within NHSScotland and publicly. Regulation could affect ability to meet regulatory requirements. Workforce: Ensuring specialist skills required to support project are secured and sustained throughout. | MMcG |  | 2 |  | 4 |  | 8 |  | The following stages of development have been subject to ICD input- - Phase 1 Development Stage 2 HAI SCRIBE- Design & Planning. - Phase 1 Development Stage 3HAI SCRIBE- Construction. - Development of Transplant Risk Assessment. Expansion Programme supported by 0.2 WTE CNM Prevention and Control of Infection providing skill set into clinical brief/clinical model/design and construction. As an interim measure all current HAI SCRIBEs developed by the Prevention and Control of Infection Nurses are submitted to the Senior User Group for review and sign off prior to works commencing. Escalated to Board and Scottish Government. |  | 1 |  | 4 |  | 4 |  | Board Microbiologist appointment in May, Microbiologist Consultant support to expansion and national appointment with sessional input to GJ |  | Bi Monthly |  | April 20 |  |  |
| S17 | If we are unable to agree a robust recovery plan and implement effectively then we may fail to maximise the capacity available at GJNH Strategic: could impact on delivery of GJF objectives and NHSScotland recovery and waiting times. Financial: financial impact associated with delayed activity and under utilisation. Reputation: Negative impact on reputation of GJF within NHSScotland and publicly. Regulation Ensuring robust governance of any new services and restart of activity, compliance with COVID-19 measures. Operational Delivery: Impact on services of continuous changes in pathways & service delivery. Workforce: Ensuring specialist skills required to support, workforce plans to support capacity. Safety/ Experiences Ensuring safety and person centred approach throughout |  | JG |  | 4 |  | 3 |  | 12 |  | Initial recovery plan proposed to Scottish Government Protocol to support pre-operative screening of elective patients in development including on site testing. |  | 1 |  | 3 |  | 3 |  | Fuller development of detailed recovery plan in progress to include governance arrangements to support any new services proposed as part of recovery plan. Development of pathways and zoning of footprint to support screening and flow of suspected COVID patients. Review of efficiencies and opportunities for improvement generated via the COVID response that can maximise delivery of services Governance structure to support monitoring of recovery plan. |  | Monthly |  | April 20 |  |
| W18 | If we are unable to provide adequate precautions, protection and support for our employees dealing with COVID-19 then the health and wellbeing of our employees may be impacted negatively Strategic: Responsibility for H&WB of staff. Financial: financial impact associated with increased absences and potential litigation if obligations not met. Reputation: Negative impact on reputation of GJF within NHSScotland and publicly. Regulation Compliance with H&S legislation and partnership standards . Workforce: higher risk of ill health, burnout and low morale Safety/ Experiences Ensuring safety and person centred approach throughout |  | GA |  | 2 |  | 3 |  | 6 |  | Gold/Silver/Bronze command and control structure. Partnership forum continues to meet to ensure good staff governance during COVID response and beyond Guidance has been provided to line managers and staff to ensure that planned leave is taken during the COVID response and in recovery to ensure staff are getting adequate time away from work. Staff rostering continues to include monitoring hours worked and ensuring appropriate working hours are maintained National guidance on risk assessing staff at risk due to underlying health conditions has been implemented and appropriate adjustments put in place to socially isolate staff or remove them from direct patient care Additional support has been put in place to provide spiritual care and mental health and wellbeing support for staff including guidance/self-help information and structured support sessions Social distancing measures have been implemented along with changes to configuration to facilities and working practices to manage COVID related risks, e.g. red and green zones |  | 1 |  | 3 |  | 3 |  | Further development of health and wellbeing support for staff |  | Monthly |  | April 20 |  |
| W19 | If we are unable to provide adequate PPE for our employees dealing with COVID-19 then the health and wellbeing of our employees may be impacted negatively Strategic: Responsibility for H&WB of staff. Financial: financial impact associated with increased absences and potential litigation if obligations not met. Reputation: Negative impact on reputation of GJF within NHSScotland and publicly. Regulation Compliance with H&S legislation and partnership standards . Workforce: higher risk of ill health, burnout and low morale Safety/ Experiences Ensuring safety and person centred approach throughout |  | GA |  | 3 |  | 4 |  | 12 |  | Daily monitoring of PPE stock levels, demand and planned deliveries to identify any projected shortfalls and escalation within board and to NHS National Procurement, including participation in twice weekly national procurement PPE teleconference. Extensive communication of current PPE guidance and correct use of PPE across organization. Contingency arrangements for PPE shortages. Ongoing programme of face fit testing including increased numbers of face fit testers trained across organisation to maximise testing capacity Guidance to line managers and staff on limiting use of PPE to required circumstances to avoid overuse Guidance to line managers to ensure any staff not currently able to use FFP3 they have been tested for to be prevented from entering high risk areas requiring FFP3 masks Reduction in planned theatre activity if PPE availability becomes critical to reduce consumption |  | 3 |  | 4 |  | 12 |  | Complete modelling of PPE consumption and predictive analysis of stock levels |  | Monthly |  | April 20 |  |
| S20 | Ongoing impact and potential of a further peak of COVID-19 pandemic across Board Strategic- impact on ability to delivery Board strategy if peak occurs with stepdown of core activity; review of delivery plans to account for COVID-19 measures. Financial: specific financial planning undertaken. Regulation: ensuring compliance with COVID-19 measures Reputation: Inability to maintain COVID light approach and ensure adequate measures for patients&staff would impact reputation. Operational Delivery: Significant change in pathways and working practices. Workforce: Increased absence, overall health & wellbeing, PPE and testing, impact of capacity variances |  | JG |  | 4 |  | 3 |  | 12 |  | Mobilisation plan signed off by SG to support immediate response including critical care capacity to support surge response. Daily reporting to SG. Command Structure and Agile Governance arrangements implemented. Regular workforce monitoring. Daily PPE monitoring and reporting. Risks specific to recovery and health & wellbeing added to Board register. |  | 2 |  | 2 |  | 4 |  | Recovery plan in development to support response over 1 – 2 years. Review of Expansion programme plans. Review wider Board strategy implementation and revise aligned to recovery plan. Hotel strategy in development to support revised operating model in light of COVID-19 restrictions. Review of Social Distancing compliance across site and development of guidance. Review of site masterplan to reflect changing footprint and SD requirements. |  | Monthly |  | April 20 |  |