NHS GOLDEN JUBILEE

SUMMARY FINANCIAL REPORT

MONTH 2

AS AT 31ST MAY 2024

FINANCIAL POSITION 31ST MAY 2024 (MONTH 2)

EXECUTIVE SUMMARY

- 2024/25 to 2026/26 FINANCIAL PLAN The NHS Golden Jubilee Board in March 2024 approved a 3 year break-even Financial Plan for the period 2024/25 to 2026/27, with considerable levels of efficiencies to be delivered (-£9.994m). The ’Achieving the Balance’ Programme is now progressing to deliver and monitor the saving work streams focussing on delivery for 2024/25 and beyond. DELIVERY OF 2024/25 FINANCIAL PLAN Current Risk Rating; High. For 2024/25 a break-even outturn position requires the delivery of -£9.944m of in-year savings /budget reductions/increased income opportunities through a combination of recurring and non-recurring measures. The Year to Date (YTD) core revenue position as at the end of May 2024 is an adverse variance of -£746k. This represents an adverse % variance of -1.89%. 2024/2025 TO 2026/27 FINANCIAL PLAN Current Risk Rating; Very High. March 2024/25 – 2026/27 Financial Plan The final 2024/25 to 2026/27 3 year plan was submitted to SG, following approval at FPC. This shows a savings requirement of (£9.944m) for 2024/25, rising to (£11.028m) for 2025/26 and (£11.481m) for the final year of the plan in 2026/27. Whilst savings plans have been developed mainly around workforce challenges, including enhanced vacancy management, review of agency costs and Waiting list initiatives, there remains a significant gap to identify in 2024/25 at this time. As work streams progress under ‘Achieving the Balance’ not all efficiency targets have been released into the position as at May, with final phasing to be agreed as part of the month 3 reporting schedule.

- 2024/25 CORE INCOME POSITION Current Risk Rating; Low. Income is £56k or 0.13% above the Financial Plan at Month 2. The main over-performance continues to be around service Cardiac and Thoracic activity for NWOS Boards. At this time not all the NES allocations have been fully agreed so there is a small level of risk for activity plans later in the year for those Boards not agreeing their full allocation.

- 2024/25 CORE EXPENDITURE POSITION Core Expenditure is -£746k or -1.89% above the Financial Plan at Month 2. PAY COSTS Current Risk Rating; Medium. In overall terms, Pay costs at Month 2 are overspent by -£107k or -0.39% above plan, primarily reflecting the pressures across medical staffing areas with the level of WLIs and agency undertaken YTD. In particular, WLI expenditure across NES Division is £127k higher in the first 2 months of the year compared with the same period in 2023/24 (an increase of almost 70%). Further analysis is provided within the relevant section of the main report. NON PAY COSTS Current Risk Rating; Very High. In overall terms, Non Pay costs at Month 2 are overspent by -£695k equating to -5.70% above the YTD budget across a number of Board expenditure categories. Whilst non-pay consumable budgets have now been re-based to reflect activity levels within the ADP, YTD over-performance and case-mix, combined with pressures within PPE and FM, as well as YTD gaps in efficiency plans account for the majority of the YTD overspend at month 2. Further analysis is provided within the relevant section of the main report.

- 2024/25 EFFICIENCY REQUIREMENT Current Risk Rating; High. There is a -£9.944m efficiency requirement within the Financial Plan to achieve the targeted break-even position for 2024/25. FULL YEAR SAVINGS PLAN The high level efficiency plan has been agreed by Work stream and is currently being taken forward within the ‘Achieving the Balance’ Programme. At this time not all targets have been taken out of the YTD position as further work is being finalised as part of the month 3 review to allocate all savings based upon agreed phasing of the work streams now in place. To-date £706k of savings have been delivered YTD with a total forecast delivery of £5.504m by the year end. Other saving schemes are yet to be finalised, but the current high level review indicates a potential in-year gap of £2.993m still to be identified. The YTD position reflects this level of unidentified savings in the system to-date.

- NON-CORE REVENUE POSITION Current Risk Rating; Low. Non-Core position at Month 2 is anticipated to be break-even (expenditure matched by SG Income).

- CAPITAL INCOME AND EXPENDITURE Current Risk Rating; Medium. Core Capital allocations of £4.637m are expected but have not been formally confirmed by Scottish Government as at the end of May. The Phasing of Phase 2 and associated Work Task Orders (WTOs) are being reviewed in light of the delayed handover of the surgical centre and a final split of required funding between 2024/25 and 2025/26 will be agreed with Scottish Government as part of Quarter 1 review. Recent meetings with SG colleagues have confirmed their intention to fund the remaining elements of this expenditure in full. The new Capital Delivery group (CDG) met in May and conducted a risk assessment of all individual capital items required across all areas of the organisation. The risk-assessed list was provided to the Strategic Capital Planning Group (SCPG) and a Capital Plan was developed for 24/25. SCPG also has recommended a £100k contingency be held for any ad hoc capital spend that may be required within the year. This plan has been taken to ELT for final approval.

FINANCIAL REPORT AT 31ST MAY 2024 (Month 2)

SECTION 1: NHS GOLDEN JUBILEE- OVERALL POSITION The table below provides the overall high level summary position of the Board as at the end of February 2024, at Month 2. The net position shows a -£746k adverse position, with over-recovery of income of £56k offsetting expenditure pressures of -£802k. It should be noted that budgets have been released from NSD service level agreements for SNAFHs and HL&D Medical Service Planning into both the income and expenditure positions, reflecting the proposed SLA values for 2024/25. Table 1 Appendix 1 provides more detail on the overall position.

SECTION 2: 2024/25 CORE INCOME POSITION Income is £56k or 0.13% above the Financial Plan at Month 2. REVENUE RESOURCE LIMIT (RRL) RRL allocations for the year at Month 2 are currently anticipated at £154.475m. At Month 2, £25.746m has been released into the position. £27.578m of the annual RRL relates to the marginal SLAs undertaken within NES for other Territorial Boards. Table 2 SERVICE LEVEL AGREEMENTS (SLA INCOME) Total SLA income is £0.072m over-recovered at Month 2. Table 3 The NSD SLA and TAVI are on target for income performance. Cardiac and Thoracic are ahead of plan by £18k and £82k respectively due to over performance in non WoS. Cardiology is under performing in non WoS by -£28k. Table 4 HOTEL AND OTHER INCOME GJ Conference Hotel income is £18k under-recovered and all Other Income sources generally on plan, with a small over-achievement of just £2k.

SECTION 3: 2024/25 CORE EXPENDITURE POSITION Total expenditure to date of £40.259m is ahead of the year to date budget of £39.457m resulting in an adverse variance of -£802k overall (-2.03%). - Pay Costs overspend of -£107k, -0.39% - Non-Pay Costs -£695k, -5.70% PAY COSTS AT MONTH 2 Table 5 – Pay Costs MEDICAL PAY COSTS The overspend in the Medical staff category is -£285k – the main drivers of overspend are within NES division with a high rate of WLI being paid this month. HL&D division has seen budget released from Medical Service Planning as well as increased funding for posts from the revised NSD SLAs. The main areas of overspends, are detailed further within the Divisional narratives. The key underlying position is due to both short and long term sickness absence and vacancies within both Consultant and Junior rotas over both HL&D and NES divisions. Divisions continue to use Agency staff and increased levels of WLIs to cover service gaps and maintain planned levels of activity. The current YTD expenditure related to WLI payments is now 50% higher than at Month 2 2023/24. As part of the efficiency programme, a work stream has been initiated to review the historic use of medical agency and WLIs in covering vacancies and recovering the activity position across both Divisions, to provide further clarity on the decisions made in incurring these significant increased costs. The key pressures within medical pay relates to medical agency costs and Waiting List initiative payment in the following areas: Table 6 – Medical staff key expenditure pressures Pressure; HLD; NES; Total. Agency:-. Radiology; -£19k; -£19k. Cardiac Registrars. Ophthalmology; -£93k; -£93k. General Anaesthetics Registrars; -£5k; -£5k. Orthopaedics. -£19k; -£98k; -£117k. Waiting List Initiatives:-. Cardiac; -£83k; -£83k. CT Anaesthetics; -£81k; -£74k. General Anaesthetics; -£120k; -£120k. Orthopaedics; -£25k; -£25k. Ophthalmology; -£43k; -£43k. General Surgery; -£120k; -£120k. -£164k; -£308k; -£472k. Grand Total of Medical Pressures; -£183k; -£406k; -£589k. These pressures are partially offset with the level of vacancy underspends across both Divisions, demonstrating the current recruitment challenges faced by the Board. NURSING PAY COSTS Nursing pay costs are underspent by £78k at Month 2. This figure is after phasing part of the Nurse vacancy efficiency saving target of £400k into the position YTD. This reflects the on-going level of vacancies across the system and the scale of the on-going recruitment challenge. Whilst this is supporting the current efficiency position, Divisions continue to work with Finance and Performance colleagues to identify recurring transformational savings plans. CLINCIAL PAY COSTS Clinical pay costs underspends are £29k at Month 2. This is after £59k of efficiency savings have been factored into the YTD position relating to the vacancy management work stream for Clinical staffing. SUPPORT PAY COSTS Support pay costs are underspent by £16k overall with pressures of -£33k relating to the Hotel activity. The other pressures are mostly within Portering and Housekeeping due to the continued additional hours worked to maintain services related to the high levels of vacancies and sickness absence but there has been a recruitment fair in Glasgow city centre which has renewed interest in the vacancies which HR are progressing. ADMIN PAY COSTS Admin pay costs are underspent by £54k at Month 2, with a small overspend of -£3k in the Hotel. Efficiencies of £35k have been identified across Corporate areas YTD, with further work required to identify further areas of efficiency in Month 3. NON PAY COSTS AT MONTH 2 Total Non-Pay costs are overspent at Month 2 by -£695k. All non-pay budgets have now been re-based to reflect the costs of activity within the 24/25 ADP. Key pressures to-date relate to the over-performance on activity plans, particularly across NES in orthopaedic joints and endoscopy and HLD across NSD SLAs. Table 7 – Non-Pay Summary PHARMACY SUPPLIES -£60K (6.22% of YTD Budget) The key areas of pressure across pharmacy supplies relates to some high cost patients treated within NSD funded services (£39k) as well as the over-performance in NES activity (£14k). Savings identified to-date relating to specific medicine switches and contract changes total £43k, with a total saving of £257k by the year end expected. SURGICAL SUPPLIES -£253k (4.3% of YTD Budget) Surgical Supplies overspend across all Division’s and the increase in costs of the consumables and devices along with the increased activity have seen this rise. Costs associated with NSD national services have only been funded at agreed 2024/25 SLA values, with pressures associated with YTD activity contributing to the over-performance YTD. NES pressures of £224k relate mainly to the over-performance on orthopaedic joint and Endoscopy activity across prosthesis, consumables and theatres. As the year progresses and a better understanding of forecast activity is provided, some additional income may be agreed to support this level of over-performance via the Topslice mechanism with Territorial Boards. (Currently the RRL for the topslice represents the activity within the ADP). LAB/RADIOLOGY SUPPLIES -£46k (15.35% of YTD Budget) NES are showing an overspend of -£13k YTD. This in the main is due to increased costs within Anaesthetics Theatres relating to Lab Costs Type 2 and disposable issues based upon the activity undertaken to-date. HL&D are showing an overspend of -£33k YTD. The main driver of this relates to Tissue Typing and SACCS Cath Lab increased use of Septal Occluders. Funding has only been provided at the level of the current SLA with NSD. PPE -£256K (14.25% of YTD Budget) NES is -£63k overspent YTD, with the key pressures across Cardiac Theatres (-£18k) and the patient coordination centre relating to service contracts (-£25k). There are also pressures across a number of ward areas on expenditure on computer hardware and small items of equipment (-£28k). Corporate is -£174k overspent YTD, with the majority of the pressures relating to maintenance and contractual works across Estates and Facilities. There are also increased pressures within EHealth relating to the purchase of computer and telecom equipment and other contractors. FM -£80k (3.3% of Annual Budget) HL&D overspend is (-£14k) – the main pressure relating to disposables, laundry and cleaning materials. NES is overspent by (-£33k) – Transport being the main overspend of (-£20k) in Hospital Ambulance service charges, General Services (-£5k) and Provisions (-£5k). The Hotel is overspent by (-£33k) YTD with the main drivers being Training (-£35k). CS&R&S £1k (0.09% of Annual Budget) There is a slight underspend showing overall divisions with the key underlying pressure relating to postage and stationery costs (-£51k) within NES driven by patient activity numbers to-date as well as increased recruitment costs relating to medical staffing (-£29k). This is offset with underspends within the Corporate areas relating to Recruitment and Professional fees (£94k).

SECTION 4: NHS GOLDEN JUBILEE- DIVISIONAL PERFORMANCE At Month 2, NHS Golden Jubilee has a Pay underspend of -£107k and a Non-Pay overspend of -£695k. The following Table provides details of these variances for both Pay and Non-Pay together with an analysis over each of the 9 Divisions (with full analysis on the relevant Appendices). Table 8 – Pay and Non-pay Variances by Division Variance Pay Costs; Variance Non Pay Costs; Total Variance. NES; -146,480; -444,272; -590,752. HLD; 26,285; -132,962; -106,677. Corporate; 31,394; -70,250; -38,856. Hotel; -36,597; -27,837; -64,434. CfSD; 0; 0; 0. NHSSA; 24,328; -24,328; 0. GJRI; 1,537; 8,821; 10,358. Reserves; 0; -2,554; -2,554. Revenue; -7,493; -1,402; -8,895. Total Expenditure; -107,027; -694,783; -801,809. - Appendix 1-Summary Finance Position (overall) - Appendix 2-National Elective Services (NES) - Appendix 3-Heart, Lung and Diagnostics (HLD) - Appendix 4-Corporate (Corporate) - Appendix 5-Golden Jubilee Conference Hotel (Hotel) (includes Income) - Appendix 6-Centre for Sustainable Delivery (CfSD) - Appendix 7-NHS Scotland Academy (NHSSA) - Appendix 8-Golden Jubilee Research Institute (GJRI) - Appendix 9-Reserves and Revenue

SECTION 5: 2024/25 RRL ALLOCATIONS AND ANTICIPATED ALLOCATIONS Table 9 – Current RRL allocations as at end May 2024 Whilst ongoing discussions with Policy teams have indicated allocations have been agreed, they have not been received in the allocation letter for Month 2 – this is not unusual as it is just the start of the financial year. However, there is an expectation that 80% of allocations will be issued by the end of June as indicated by a Letter from Richard McCallum earlier in the year.

SECTION 6: 2024/25 EFFICIENCY REQUIREMENT There is a -£9.944m efficiency requirement within the Financial Plan to achieve the targeted break even position for 2024/25. Full Year Non-Recurring Savings Plan The proposed Work stream Programme was approved by ELT in May which is summarised below, identifying the level of savings planned against each work stream against each Division: Table 10 Work has progressed on a number of work streams detailed in the table above, focussing on workforce management, Medicines and Procurement to-date. Significant opportunity exists across HLD in particular in reviewing procurement savings across a wide range of consumables, with the HLD Value programme identifying a number of areas of focus that could deliver in the region of £1.3m by the year-end. To-date only areas that have definitively identified savings in the YTD position have been removed from the YTD budget, as more robust plans are developed to agree the phasing of savings for the remainder of the year. The table below provides a summary of savings taken YTD with the corresponding forecast savings by the year-end. Table 11 As part of the Q1 review, a full phased efficiency plan will be factored into the Divisional budgets reflecting the level of savings to be identified by the year-end. Corporate flexibility opportunities will also be factored into the overall efficiency plan whilst work streams progress and identify the necessary schemes for delivery. Whilst the focus will remain on identifying recurring, transformational schemes, there will be a reliance on non-recurring solutions again this year to allow full recurring options to be developed. Sustainability & Value Achieving the Balance Programme has been integrated to the Board’s reporting structure, reviewing all work streams for progress and update on risks and recurring delivery. The revised governance arrangements in place ensure all schemes are reviewed regularly to highlight all opportunities. All areas identified within the ’15 box grid’ have been built into the work stream areas the Board is progressing. In particular a review of temporary staffing expenditure across all staff groups has identified the current level of expenditure associated with funded vacant posts, as well as costs incurred to recover the Waiting Times Targets. Reviews of Pharmacy costs with the Director of Pharmacy have identified savings to date that will deliver £257k by the year end, with further work focussing on reducing variation, optimising dispensing and reducing the quantity of discharge medicines being finalised. Procurement and finance have created a detailed analysis tool to investigate the highest areas of expenditure where there will be opportunities to review current procurement and product mix across all specialties. This has already supported the work undertaken in HLD in identifying potential savings across many areas. Further work is required to review similar areas across NES Division. This work will support the revised governance arrangements associated with ‘Achieving a Balanced System’.

SECTION 7: NON CORE PERFORMANCE Non-Core position at Month 2 is anticipated to be break-even (expenditure below matched by SG Income. Depreciation and AME elements will be reviewed as the year progresses to ensure Non-Core funding is increased to match any changes in-year. The main elements of Non-Core funding are shown in the table below: Table 11 Category; Annual Budget £. Annually Managed Expenditure (AME); 227,000. Depreciation (Donated Assets); 8,000. Depreciation (Board Capital); 11,472,000. Depreciation (Leases); 1,104,000. Total; 12,811,000.

SECTION 8: CAPITAL INCOME AND EXPENDITURE Capital allocations of £4.637m have been confirmed by Scottish Government in meetings held in June, but with no formal allocation letter received to-date. The Table below provides a summary of the anticipated Core Capital Allocations for 2024/25. Table 12 Expected Allocation. Allocations; £m. Formula Core Capital; 2.691. 23/24 Slippage; 1.246. Lifts; 0.7. Total Core Allocation; 4.637. Phase 2; tbc. Phase 2 Equipment; tbc. Total Phase 2 Allocation; 0. With the delay in the formal hand-over on the newly built surgical centre, Finance in liaison with the Director of Estates and the Board’s cost advisors are finalising the phasing of the Phase 2 remaining works and associated Work Task Orders between 2024/25 and 2025/26. Based on the above, the following is the Capital Expenditure Plan split across the various monitoring categories. Table 13 Category; Capital Plan. £m. Estates; 3.440. Medical Equipment; 1.050. Information Management and Technology; 0.047. Contingency; 0.100. Total Planned Core Capital; 4.637. It is anticipated that the allocation letter for Core CRL will be received by Q1

Decision– (1) Approve the Summary Financial Report as at 31 May 2024 (Month 2)

Graham Stewart

Interim Director of Finance

NHS Golden Jubilee

APPENDIX 1 – SUMMARY FINANCE POSITION

INCOME

EXPENDITURE

APPENDIX 2 DIVISIONAL ANALYSIS - NATIONAL ELECTIVE SERVICE (NES)

Analysis of the Division NES is overspent by -£591k between Pay and Non Pay costs with the following key variances: Medical Staffing -£310k The key pressures across the Division YTD relate to agency and WLI costs associated with the following:- General Anaesthetics - £59k General Surgery - £109k Orthopaedics - £164k Phase 2 appointments continue to be made. Nursing Staffing £54k This is showing a favourable position after £300k was removed to Efficiency Savings – this reflects the continued recruitment situation of vacancies. Surgical Supplies -£224k Funding has been released to the division but as the total activity plans have yet to be agreed within the ADP, further work is needed once they have been finalised to release the accurate funding to the division. There has been an increase in activity over the first two months of this year.

APPENDIX 3 DIVISIONAL ANALYSIS - HEART, LUNG AND DIAGNOSTICS (HLD)

Analysis of the Division HL&D is overspent by -£107k between Pay and Non Pay costs the following key variances: Medical Staffing -£1k Starting off strong at the start of this financial year with budget released for SNAHFs Business case, Flow Beds and the Medical Service Planning which now shows the correct funding for the majority of the medical specialties. There continues to see the use of Agency and WLI being used to cover sickness and vacancies at a cost of £183k YTD. Pharmacy Supplies -£39k There was additional budget released to cover the NSD cost pressures and inflation in this division but the first part of the efficiency savings for the work stream programmes has been input this month for the division. Surgical Supplies -£191k Although budget has been released to cover the variable costs for the SNAHFs business case, it should be noted that the funding will not cover the full year’s costs of the agreed increased activity so ongoing robust control is needed to ensure we are aware of the pressures.

APPENDIX 4 DIVISIONAL ANALYSIS - CORPORATE

Analysis of the Division Corporate is over by -£39k between Pay and Non Pay costs with the following key variances: Support Staffing - Breakeven Budget has been released to cover all the areas within this category and Phase 2 funding has been given to cover all the new starts. There has recently been attendance by GJ at a recruitment fair for in central Glasgow which was very successful and HR are currently working through the names to arrange interviews. Admin Staffing - £4k HR have also seen budget released to cover the different working schemes that are happening within GJ – International Recruitment, Phase 2 posts and E-Rostering. This has seen the cost pressures being covered. E-Health have recruited to vacancies and this has resulted in a decrease in the pressure in consultancy costs to support key projects being reduced. PPE -£164k The main driver in this area is cost pressures within EHealth due to purchase and service of computer and telecom equipment to meet the ongoing recruitment and upgrade of various services with GJ.

APPENDIX 5 DIVISIONAL ANALYSIS - HOTEL

Analysis of the Division – The hotel is budgeted at a deficit of -£1.046m (variances compared to this position) The Hotel Pay is overspent by -£37k, Non Pay -£28k and Income under performed at £18k resulting in a Month 2 cumulative overspend of -£82k. The following key variances: Income £18k - Income is under recovered with the main elements being Rooms and Conferences at the start of the season. Expenditure -£679k overspend, reflecting the pressures across Utilities, Catering and Pays in delivering the level of income YTD

APPENDIX 6 DIVISIONAL ANALYSIS - CfSD

Analysis of the Division No financial issues to be reported as the Funding related to CfSD will reflect the outturn position by year-end.

APPENDIX 7 DIVISIONAL ANALYSIS - NHS SCOTLAND ACADEMY

Analysis of the Division No financial issues to be reported, although work continues with the Director of the Academy to firm up the forecast funding requirement for 2024/25.

APPENDIX 8 DIVISIONAL ANALYSIS - GOLDEN JUBILEE RESEARCH AND DEVELOPMENT

Analysis of the Division No financial issues to be reported other than a vacancy currently in the process of being filled.

APPENDIX 9 DIVISIONAL ANALYSIS - GOLDEN JUBILEE RESERVES AND REVENUE

REVENUE

Analysis of the Division This area includes reserves and contingency budgets agreed within the Financial Plan. No financial issues to be reported.