Ref: GJF/2017/12/08

# Board Meeting:		7 December 2017

# Subject:	Business Services Patient Activity Performance Report – October 2017

Recommendation:	Board members are asked to discuss and note patient activity performance

__________________________________________________________________

## 1	Background

Patient activity is reported on a monthly basis, both by month and year to date.  Data is primarily measured in episodes of care.  However, data is also captured to reflect the number of procedures being carried out by Board, by specialty.  This information is particularly relevant to referring Boards who are allocated activity and measure their activity/throughput at the Golden Jubilee National Hospital (GJNH) in numbers of procedures.

Appendix A to this document is provided for information purposes and reflects the number of patients treated against an annual plan of 16,546 (patients).

Appendix B to this document is adjusted to represent theatre slots used (as opposed to numbers of patients) in both orthopaedic surgery and plastic surgery.  This allows us to more accurately reflect actual theatre utilisation and allows us to focus on maximising the theatre capacity that is available to us.

Referring Boards receive a monthly monitoring document which provides them with a detailed breakdown of the number of patients referred, their complexity and the number of theatre slots used to treat them.

2	Operational Governance

2.1	Inpatient/Day Case/Diagnostic Imaging Activity Analysis October 2017

Activity for inpatients/day case procedures measured against a projection of 16,621 (which excludes cardiothoracic/cardiology activity) was behind plan by 3.3% for the month of October when activity is adjusted to reflect complexity (Appendix B), and 5.4% behind the full year to date plan.

Measured against a total activity projection of 46,071, the combined inpatient/day case and imaging activity at the end of October was ahead of plan by 5.5% for the month of October when adjusted to reflect complexity (Appendix B) and 0.4% behind the full year to date plan.

3	Analysis of Performance Against Plan at End October 2017

3.1	Orthopaedic Surgery

The annual target for orthopaedic joint replacements for 2016/17 is based on 3,803 primary joint replacements.  This number is calculated on the basis of one patient to one theatre slot.  Each session equals two primary joint theatre slots.  However, based on experience over the recent years, we have made the assumption that the number of complex joint replacements likely to be referred for treatment would be approximately 9%.  These procedures typically take the equivalent theatre space of 1.5 - 2 primary joint replacements.

In addition to the 3,803 primary joint replacements, there is a target number of 681 orthopaedic non-joint procedures and 550 foot and ankle procedures for the year. This equates to a total of 5034 orthopaedic theatre slots per annum (as documented in Appendix B).

At the end of October, orthopaedic joint activity was ahead of the year to date plan by 103 primary joint replacements and 67 foot and ankle procedures although behind by 98 other ‘non joint’ procedures (which consists of intermediate/minor procedures such as Anterior Cruciate Ligament repair, arthroscopy etc).  Throughout 2017, there continues to be a higher than expected demand for foot and ankle surgery and lower orthopaedic ‘other’ than expected.  Overall, orthopaedic surgery is currently ahead of the full year plan by 69 procedures/theatre slots.

3.2	Ophthalmic Surgery

Ophthalmology activity was 81 procedures behind plan for the month of October.  The ophthalmology year to date shortfall is currently 396 procedures.  This continues to be primarily due to consultant availability.

3.3	General Surgery

General surgery performed in line with the monthly target in October and is also slightly ahead of the year to date plan. There have been recent requests from Boards for additional activity, so the service is exploring the potential to provide weekend operating lists.

3.4	Plastic Surgery

For reporting purposes, Plastic Surgery has been split and will be monitored throughout 2017/18 as hand surgery, minor plastic surgery and major plastic surgery. Hand surgery was ahead of plan the month of October by 12 procedures.  Minor and major plastic surgery procedures were slightly behind plan.

3.5	Endoscopy

The endoscopy service performed ahead of plan by 10 procedures in the month of October.

3.6	Diagnostic Imaging

Staffing the new ultrasound machine continues to be a challenge. However, a number of interim solutions have been put in place to manage this. Activity has remained high and the service has over performed by 262 examinations in October and remains ahead of the year to date plan by 407 examinations.

- Current Situation

- Orthopaedic activity remained high in the month of October.  There continues to be a focus on the continued development of the ‘Orthopaedic Enhanced Monitoring Unit’ which accommodates complex patients with additional needs or extended lengths of stay. Once fully operational, this unit is expected to reduce the reliance on High Dependency Unit beds for complex patients.

- Following a discussion with the referring Board and a detailed review of hand surgery procedures carried out to date, it emerged that the complexity of procedures being carried out by our specialist hand surgeon had not been captured in our activity reports. This detail has been shared and agreed with the referring Board. Activity numbers have subsequently been adjusted in this month’s report to reflect complexity and number of theatre slots used for these cases. This adjustment was highlighted to and agreed as an appropriate way forward by the Senior Management Team.

- Discussions are continuing with the Ophthalmic Consultants on a regular basis to explore every opportunity that may exist to recover the significant shortfall in ophthalmology.

- There is a shortfall of 122 scopes year to date.  Additional theatre capacity is being made available and we remain optimistic that the shortfall will be recovered by the year end.

- Building work is complete and the two new MRI scanners have now been installed on site.  Radiographers have been recruited and are currently being trained to operate the new equipment.  The new unit is expected to go live in the week commencing 4 December.

5	Conclusion/Recommendation

Board members are asked to discuss and note patient activity performance.

June Rogers

Director of Operations

28 November 2017