CfSD Assurance Statement

| Meeting: | NHS Golden Jubilee Board | Responsible Executive: | Katie Cuthbertson |
| --- | --- | --- | --- |
| Date of Meeting: | 27 November 2025 | Report Author: | Russell Scott |
| Submission Date: | 21st October 2025 | Period Covered by Report: | Upto end of September 2025 |

Part 1: Programme Team Updates

| Programme: | Modernising Patient Pathways |  | Total Workstreams: |  |  | 9 |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Actions this Period | Planned Actions for Next Period | Workstreams RAG status: |  |  |  |
| Driving transformational and sustainable change to improve planned care patient access and outcomes across NHS Scotland | - This year to date, over 113k appointments had been saved through the use of ACRT, and 37k patients have been placed on a PIR pathway. - Published NHS Inform page to support forthcoming hand osteoarthritis page. - Ongoing work on competency frameworks for Dermatology and Urology specialist nursing, and respiratory advanced practice physiotherapy. - Dermatology competency framework approved by SDG. - SDG meetings for Cataract, Critical Care, Dermatology, ENT, Gastroenterology, Neurology, Rheumatology, Urology and Vascular Surgery. | - Submit severe asthma pathway for sign off and publishing. Re-approval of national headache pathway updated in line with SIGN guidance - Plan dermatology RDS pathway webinar on 6/11/25. - Launch patient focussed booking (PFB) data capture pilot with 3 Boards. - Ongoing work on nursing/AHP competency frameworks to support role development and succession planning (Dermatology, Urology, Physiotherapy) - Digital Dermatology: Project has now exited ANIA and will be overseen by MPP Programme Team who will provide ongoing national support from October. - Complete Strategic Needs Assessment to inform Target Operating Model for Gynae. | Red | Amber | Green | Other |
|  |  |  |  | 2 | 7 |  |
|  |  |  | RAG notes: |  |  |  |
|  |  |  | - A Development of National Pathways: Following national pathways approval there is a risk of delays in publishing on websites. - A Measurement & Analysis: Limited Board engagement on Heatmap submissions including Pathway adoption, due to capacity issues arising from supporting planned care performance arrangements. - Other workstreams are green. |  |  |  |

| Programme: | National Elective Co-ordination Unit |  | Total Workstreams: |  |  | 6 |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Actions this Period | Planned Actions for Next Period | Workstreams RAG status: |  |  |  |
| Support the development of a national elective co-ordination unit, including the transition to an operational model, which will support Boards with their current planned care waiting lists. | - Continued national waiting list patient validation: 67,541patients validated this year to date. - National waiting list validation campaign finalised for 1 Board. - Patient treatment capacity campaigns: treated 1,748 patients year to date across various specialities. - Coordinated ongoing National Dermatology campaign in 2 Boards with 1 provider Board. Finalised image triage for remaining patients in 1 Board. - Reviewed Diabetes Closed Loop System (CLS) team processes, roles and responsibilities and engaged in discussions regarding final destination for CLS team with Scottish Government. | - Continue to undertake national waiting list validation in 2 Boards, and start validation in another 2 Boards. - Coordinate ongoing National Dermatology campaign in 1 Board with 1 provider Board. - Ongoing planning for the National Dermatology campaign in another Board. Engage with SG regarding priority Boards for the Dermatology campaign. - Work with SG Digital Health & Care and Microsoft to develop an integrated digital system for NECU. - Finalise transfer plan for CLS team. | Red | Amber | Green | Other |
|  |  |  |  |  | 5 |  |
|  |  |  | - All workstreams are green. |  |  |  |

| Programme: | National Unscheduled Care Improvement |  | Total Workstreams: |  |  | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Actions this Period | Planned Actions for Next Period | Workstreams RAG status: |  |  |  |
| Define best practice in key areas within Unscheduled Care (UC) and support Boards to improve the patient and staff experience and the timeliness and safety of patient care | - Transitioning of unscheduled care performance function to CfSD from Scottish Government commenced - Issued first data analysis packs to Boards to support development of improvement plans in support of improved 4 hour performance. - Continued development of leverage points analysis for all Boards to support improvement planning - Carried out on site Board visit to 1 Board with report and recommendations provided. - Held national discussion forum for community palliative care. The group aims to identify gaps in current referral practices, particularly for non-cancer patients with a view to defining best practices for community based palliative care. - Continued data analysis for palliative care pathways and care home data. - Flow Navigation Phase 1 closure report distributed nationally to all Boards. - Drafted Same Day Emergency Care (SDEC) guiding principles document to be circulated to SDEC SLWG. - Continued Board benchmarking to identify where additional support is required. | - Continued transition of the performance function to CfSD - Continue data analysis for palliative care pathways and care home data. Issue palliative care survey and collate feedback, which will aid further topics to be raised and discussed in the National Discussion Group. - Hold national discussion group re: access to end-of-life drugs for care home residents. The group have agreed to undertake deep dives with selected volunteer Boards and Scottish Care/ Marie Curie to understand non- admission ED attendances and explore good practice. - Support Flow Navigation expansion Test of Change in 1 Board. - Will hold Flow Navigation Regroup event on October 7th at NHS Lanarkshire, to share insights from Boards, SAS and NHS24. - Finalisation of SDEC guiding principles to the UC SLT, following group approval from the SDEC SLWG. - Support for Boards to Implement Whole System Operating Framework. | Red | Amber | Green | Other |
|  |  |  |  | 1 | 4 |  |
|  |  |  | - A Flow Navigation: SDG is being paused while Phase 2 work is scoped. - Other workstreams are green. |  |  |  |

| Programme: | Cancer Improvement and Earlier Diagnosis Programme |  | Total Workstreams: |  |  | 8 |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Actions this Period | Planned Actions for Next Period | Workstreams RAG status: |  |  |  |
| Reduce the proportion of later-stage cancers (stage III and IV) diagnosed over the next 10 years, with a focus on those from areas of deprivation. | - Continued development of next 3-year Cancer Action Plan (2026-2029) which will support operational delivery of the National 10-Year Cancer Strategy. - Continued to support Boards with backlog clearance and improvement plans. - Supported Cancer Programme Delivery Board and associated improvement plans. - Finalised toolkit for the Framework for Effective Cancer Management. - Submitted scoping paper to SG regarding Cancer Waiting Times review. - Latest “Be the Early Bird” public awareness campaign went live. - Colorectal optimal cancer diagnostic pathway published and available on Right Decision Service. | - Will continue further development of Cancer Action Plan 2026-2029. - Continue to support Boards with backlog clearance and improvement plans. - Review of ToR and membership due to new BCE taking up chair and increased scrutiny of cancer waiting times by the First Minister. - Will look to agree chair, project steering group and project timeline for the clinical review of cancer waiting times (following formal commission from SG.) - Publish Framework for Effective Cancer Management on Right Decision Service. - Hold Detect Cancer Earlier roadshows targeting areas of deprivation. - Finalise communications plan for the Gateway C primary care education platform. - Develop “lessons learned” document following the clinical review of the Scottish Referral Guidelines for Suspected Cancer. | Red | Amber | Green | Other |
|  |  |  |  |  | 8 |  |
|  |  |  | - All workstreams are green. |  |  |  |

| Programme: | National Endoscopy Programme |  | Total Workstreams: |  |  | 6 |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Actions this Period | Planned Actions for Next Period | Workstreams RAG status: |  |  |  |
| Supporting the ongoing delivery of the Endoscopy and Urology Diagnostic Recovery and Renewal Plan | - Endoscopy Reporting System (ERS) user group have completed testing of new system and collated list of issues to be discussed with NSS. - SBAR submitted to SG recommending that NHS Scotland uses data analytics from the National Endoscopy Database, instead of the ERS into the SEER platform and that funds are reassigned to support this work. - Worked with Right Decision Service to progress publication of the Endoscopy toolkit. - Closing date for non-medical endoscopists training places has been extended into Oct due to not securing sufficient uptake. - Carried out physical visit to 1 Board to support reduction in Did Not Attends (DNAs). | - Work with Boards to promote use of refreshed qFIT consensus document to validate waiting lists. - Will support NSS who will met with ERS supplier to discuss current issues and concerns raised by user group. - Continue to monitor waiting times and provide feedback to Boards. - Work with 2 Boards to support training needs for non-medical endoscopists. - Continue to progress publication of the Endoscopy toolkit. - Hold in-person visit with 1 Board to support development of Endoscopy plan. | Red | Amber | Green | Other |
|  |  |  | 1 |  | 5 |  |
|  |  |  | - R Implementation of Endoscopy Reporting System (ERS): Some Boards have been told that their version of the Endoscopy Reporting System can no longer be supported. We are supporting NSS who are discussing situation with supplier. - Other workstreams are green. |  |  |  |

| Programme: | Innovation |  | Total Workstreams: |  |  | 11 |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Actions this Period | Planned Actions for Next Period | Workstreams RAG status: |  |  |  |
| Facilitate the rapid assessment of new technologies for potential national adoption and lead the accelerated implementation of approved technologies across NHS Scotland. | - Digital Dermatology: 100% of GP practices now have access to the digital application. - Diabetes Prevention and Ambulatory ECG Patches: funding for both innovations has now been approved by SG. - Pharmacogenetics: recruitment is ongoing, and pre go-live meetings beings held with Boards. - Diabetes Remission: clinical leads have been recruited. Procurement evaluation consensus meetings completed and preferred supplier identified. Drafted benefits realisation strategy. - Chest X-Ray AI: technical design and costing behind schedule as PACS team are focussed on delivery of their core programme. IDA have been updated and agreed delay in value case delivery. Team have adjusted timeline and will focus on delivery of other workstreams. | - Pharmacogenetics: start testing for both CYP2C19 Genotype and Neonatal Gentamicin projects. - Diabetes Remission: Onboarding of clinical leads and project manager. Hold meetings with digital partners re: SCI Gateway configuration. - Diabetes Prevention and Ambulatory ECG Patches: establish Programme Delivery Boards and prepare for project recruitment. - Intelligent Liver Testing and Obstructive Sleep Apnoea: hold stakeholder meetings to understand Board needs. - Chest X-Ray AI: continue to progress elements of value case that are not dependent on PACS team. - Submit benefits report to IDA in support of Digital Dermatology | Red | Amber | Green | Other |
|  |  |  |  | 3 | 7 | 1 |
|  |  |  | - A Chest X-ray AI (CXR AI): There is a dependency in support of the Chest X-Ray AI innovation that the National PACS team need to focus on deployment of new PACS system. - A Pharmacogenetics: Delays in getting purchase order approval for testing machines. - A Diabetes Remission: Delays in getting Data Privacy Impact Assessment approved in 2 Boards. One has since been resolved. - O Digital Dermatology workstream is now completed. - Other workstreams are green. |  |  |  |

| Programme: | NHS Green Healthcare Scotland |  | Total Workstreams: |  |  | 7 |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Actions this Period | Planned Actions for Next Period | Workstreams RAG status: |  |  |  |
| Improve and evidence environmental sustainability across NHS Scotland | - Approval for Programme Expansion to NHS Green Healthcare Scotland (which will include Theatres, Renal and Endoscopy programmes) - Use of sulphur hexafluoride and perfluoroethane in vitreoretinal surgery: gathered clinical input to inform next steps. - Hospital wide surgical vacuum: developed academic paper to promote inefficiencies in current systems. Will be used to help inform changes to future Scottish Health Technical Memorandum. - 7 bar surgical air systems: carried out mapping of the current state of system use to identify feasibility and scale of future opportunity. - Reusable laparoscopic ports and instruments: continue current trials. Started to explore opportunities to expand trials. - Introduce reusable textiles: present paper to SG Resource Stewardship Group - Reusable hover mattresses: NSS ARHAI team reviewed action to ensure it incorporated infection prevention and control (IPC) considerations for cleaning. The action was then updated with guidance to ensure Boards adopted the action safely. | - 7 bar surgical air systems: will continue mapping of current landscape. Boards to submit responses by end of October. - Hospital wide surgical vacuum: will continue to develop academic paper with intention of submitting to a medical journal. - Reusable laparoscopic ports and instruments: support current trials and explore opportunities to expand trials. - Reusable Hover Mattresses and Block Rooms: prepare to publish actions on CfSD website. - Will commence rebranding/messaging from Green Theatres Programme to NHS Green Healthcare Scotland. - Start to develop overarching strategy for Green Healthcare Scotland. | Red | Amber | Green | Other |
|  |  |  |  | 2 | 5 |  |
|  |  |  | - A Identify, develop and release carbon saving actions: Some delays in progressing carbon saving actions due to local Board capacity issues limiting clinical input and supporting data. - A Deploy measurement plan to support progress and demonstrate impact: Some Boards have not engaged with current cycle of measurement meetings. - Other workstreams are green. |  |  |  |

| Programme: | Planned Care Programme |  | Total Workstreams: |  |  | 23 |
| --- | --- | --- | --- | --- | --- | --- |
| Objectives | Actions this Period | Planned Actions for Next Period | Workstreams RAG status: |  |  |  |
| Enhance the delivery of planned care, by facilitating initiatives designed to improve demand and capacity, promote greater elective activity and address waiting times. | - Waiting Times: continued support of SG’s "weekly rhythm" re: 52 week wait clearance reporting and analysis. - National Orthopaedic Plan: discussed with Deputy Chief Medical Officer for review. - National Treatment Centres: continue monitoring NTC capacity and performance. - Allocated final tranche of additional Trauma and Orthopaedic funding to Boards. - Held Scottish National Audit Programme governance discussions with Boards - Continued roll out of Ophthalmology Electronic Patient Record (EPR) across West of Scotland. - Worked with Boards to increase cataract activity via in-sourcing and waiting list initiatives supported by SG funding. - Continued to support expansion of National Ultrasound Training Programme. | - Continue leading weekly meetings with Boards to focus on clearance of 52wk+ waits and reporting to SG Planned Care waiting times governance structure. - Work with Boards to ensure that SG funded initiatives are implemented and delivered. - Continue to monitor and manage NTC capacity and performance. - Submit updates against National Orthopaedic Plan, National Imaging plan and National Ophthalmology Plan. - Continue to develop NHS Inform page about key orthopaedic conditions and after-care. - Review Ophthalmology EPR progress against trajectory and patient outcome data with Boards and NSS Product Lead. - Continue to monitor implementation of Cataract Blueprint, particularly re: ongoing theatre staffing challenges. | Red | Amber | Green | Other |
|  |  |  |  | 2 | 20 | 1 |
|  |  |  | - A Ophthalmology Electronic Patient Record: Delivery behind target but mitigations being implemented. - A Cataract Surgical Throughput: Ongoing issues with Theatre upgrades in 1 Board. Potential solutions have been identified. - O Scottish Strategic Network for Diagnostics meetings have been paused pending Network review. - Other workstreams are green. |  |  |  |

| Workstream RAG status: Definition |  |  |  |
| --- | --- | --- | --- |
| Red | Amber | Green | Other |
| Workstreams shown as red have a significant risk to delivery than cannot be managed within existing resources. There is a likelihood that key elements of the work will not be achievable and may need to be amended. | Workstreams shown as amber have a risk to delivery, but this risk can be managed within existing CfSD resources. There is a need to take corrective action and/or agree necessary changes to the planned outcomes. | Workstreams shown as green are on track and are expected to be completed on time (or ahead of schedule) and will achieve the expected outcomes. Any issues are minor and readily correctable. | Some workstreams may have a different status. This includes workstreams which are completed, paused, or not yet started. |

Part 2: Summary of Key Strategic Risks and Issues

| Issues |  |  |
| --- | --- | --- |
| Description | Mitigation | Score |
| (I10) There is an issue in regard to not having confirmed baselined recurring (annual) funding for Core CfSD Workforce Costs by the Scottish Government (Ref (B004/22 on Corporate Register) | Holding regular engagement with SG to seek obtaining letter of comfort around budget/finances in support of CfSD commission. GJ Finance team have conducted baseline funding assessment for Core CfSD staffing. Advocate for Multi-year Funding. Demonstrate Value and Impact. | High |
| (I8) Resources constraints in PHS mean that CfSD is unable to provide analysis, data collection or reporting. | Update: Have progressed developing work plan for funded CfSD activity 25/26. SOP developed and endorsed to support coordinated approach on Information Requests, to avoid overlap, duplication and to support maximising PHS resources. Level 2 Discovery access granted to CfSD staff resulting in reduced data and management information requests. Issue now re-assessed and no longer High impacting | Med |

| Risks |  |  |
| --- | --- | --- |
| Description | Management / Mitigation | Score |
| (R10) There is a risk that CfSD is not seen as a distinct body due to unclear demarcation between CfSD, the GJ and SG. This could limit its autonomy and shift its perception from a national improvement body to a performance management organisation. | Risk is currently accepted. Within workplan clearly indicate performance monitoring and not management. Developing MOU with SG colleagues. Use Board Engagement meetings to reinforce distinction between CfSD performances monitoring against SG’s management. Clarity of CfSD role/purpose. Define and Differentiate Service Improvement and Performance Management Activities | High |
| (R11) There is a risk that the gap to reduce waits > 52 weeks by March 2026 remains and will cost more to contract Independent Sector Dermatology consultant capacity to close the gap if there is limited/no consultants offering support for virtual photo triage at NHS additionality rates. | Create optimal conditions for NHS consultants to easily engage in virtual photo triage out with core working hours. NECU is facilitating the model for virtual photo triage with NHS Forth Valley to primarily support NHS Lothian to reduce their backlog of patients > 52wks | High |