| # Board Meeting: | # 26 Sept 2019 |  |
| --- | --- | --- |
| # Subject: | # GJF Programme Board |  |
| # Recommendation: | # Board members are asked to: # Discuss and Note. # Discuss and Approve. # Note for Information only. |

## 1	Background

This paper provides an overview of progress to date with regards Phase 1 of the hospital expansion programme.

The format of the paper was agreed by the Programme Board as the standard monthly reporting template.

2	Proposals

The paper:

- provides a programme update

- provides a commercial summary;

- provides an update on the design status;

- provides an update on works on site

- provides an update on community benefits;

- provides a summary of the key risks and mitigation;

- provides a summary of the programme budget;

- provides a summary of issues affecting the programme;

- provides an update on communication and stakeholder engagement;

- sets out key tasks going forward

## 3	Option appraisal/risk assessment

n/a

### 4	Consultation

n/a

5	Resource implication

n/a

6	Conclusion/Recommendation

The Board is asked to acknowledge the overall progress to date made with Phase 1 of the hospital expansion programme.

Jann Gardner

Chief Executive

19 Sept 2019

(John M Scott, Programme Director)

| Overview | Status | Green |
| --- | --- | --- |
| Key milestones within this reporting period include: - The Cabinet Secretary visited the site on 26th August 2019 |  |  |

| Progress Summary | Status | Green |
| --- | --- | --- |
| Programme Update The project remains on programme to complete on the Planned Completion Date of 7th May 2020 (N.B. Contractual Completion Date is 15th June 2020). Commercial Summary No commercial issues. Design Status Final interior design proposals are awaited from the PSCP and dialogue is ongoing on the final way finding proposals. Both these items will be brought to a future Senior User Group meeting for sign off. Statutory Approval Status Stage 1 Building Warrant has been approved by WDC. Stage 2 Building Warrant application has been submitted. Stage 3 Building Warrant Application has been submitted. Following approval of the Stage 1 Building Warrant the Building Control Officer has visited the site on six occasions from April to July 2019 to inspect the works. Works On Site Complete: - Piling works - Services alteration works - Drainage works - Foundation works - Floor slabs - Steelwork - Metal decking and stud welding - Pre-cast stairs Ongoing: - Procladd almost complete on roof - SFS almost complete - Brick & blockwork has commenced - Rainscreen and cladding has commenced Community Benefits Kier attended the Programme Board in May 2019 and provided a full update on all aspects of community benefit progress. Key Risks and Mitigation The risk register was fully reviewed and updated for inclusion in the FBC. Further risks have been identified since and an update will be provided to the Programme Board. |  |  |
| Programme Budget | Status | Green |
| A full update is provided within the Cost Control Report – August 2019. |  |  |
| Issues Affecting the Programme | Status | Amber |
| Provision of Consultant Microbiologist input. A possible solution is being explored to provide the input via a private consultant. A meeting has been set up to discuss our requirements with the consultancy on 11th September 2019. In parallel an advert is being prepared to go to the market if required. |  |  |
| Communications and Stakeholder Engagement | Status | Green |
| # The Cabinet Secretary visited the site on 26th August 2019 and met with the Programme Team, Volunteers and Ophthalmology staff. |  |  |
| Key Tasks for between now and next reporting period |  |  |
| Key tasks for the forthcoming period include: - Progress Building Warrant Stage 3 approval Works On Site - Continue brickwork/blockwork - Continue installation of windows - Continue installation of curtain walling - Continue installation of rainscreen and composite cladding - Commence fit-out/partition works |  |  |

# John M Scott

# Programme Director

# 12th September 2019